## Product Backlog
Planned Sprint | Actual Sprint | US ID | User Story Description | MOSCOW | Dependency | Assignee | Status
S1 | S1 | US1 | Setup Python environment and project structure | MUST HAVE | Done | Rutuja | 3- Completed
S1 | S1 | US2 | Understand multiprocessing and text handling concepts | MUST HAVE | US1 | Rutuja | 3- Completed
S2 | S2 | US3 | Develop Text Breaker to split large datasets | MUST HAVE | US2 | Rutuja | 3- Completed
S2 | S2 | US4 | Implement Loader for CSV/TXT files | MUST HAVE | US3 | Rutuja | 3- Completed
S3 | S3 | US5 | Build Rule-based sentiment scoring system | MUST HAVE | US3 | Rutuja | 3- Completed
S3 | S3 | US6 | Implement search and filtering functionality | SHOULD HAVE | US5 | Rutuja | 3- Completed
S3 | S3 | US7 | Enable CSV export and reporting | SHOULD HAVE | US6 | Rutuja | 3- Completed
S4 | S4 | US8 | Optimize database using indexing | MUST HAVE | US5 | Rutuja | 3- Completed
S4 | S4 | US9 | Improve storage and query performance | SHOULD HAVE | US8 | Rutuja | 3- Completed
S4 | S4 | US10 | Integrate email notification system | COULD HAVE | US7 | Rutuja | 3- Completed
Note on F1: ====== ID#AAABcShYZQo Sumeet Kumar Barua08 (2025-01-27 09:44:41) Mention the US ID(s) on which the user story depends.

## Sprint Backlog
NOTES: Task sizing should be between 0.5 to 12 hours
US ID | Task ID | Task Description | Task Start Date | Task Completion Date | Team Member | Activity | Status | Original Estimate Effort (In Hours) | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14
[8 empty] | 87 | 5 | 6 | 10 | 10 | 7 | 5 | 5 | 6 | 4 | 5 | 6 | 6 | 6 | 6
SPRINT 1 BACKLOG
US1 | T1 | Setup Python environment & install libraries | 2026-02-09 | 2026-02-11 | Samiksha | Setup | 3-Completed | 5 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US1 | T2 | Study multithreading and parallel processing concepts | 2026-02-10 | 2026-02-13 | Samiksha | Learning | 3-Completed | 6 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0
US2 | T3 | Learn text preprocessing and regex basics | 2026-02-12 | 2026-02-14 | Samiksha | Learning | 3-Completed | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0
US2 | T4 | Design system architecture and data flow | 2026-02-15 | 2026-02-17 | Samiksha | Design | 3-Completed | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 2 | 1 | 1 | 1 | 1 | 0 | 0
US2 | T5 | Setup SQLite database and test basic operations | 2026-02-18 | 2026-02-20 | Samiksha | Development | 3-Completed | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1
US2 | T6 | Prepare sample datasets and initial file loader | 2026-02-20 | 2026-02-22 | Samiksha | Development | 3-Completed | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1
SPRINT 2 BACKLOG
US3 | T7 | Develop parallel text chunking module using thread pool for efficient data processing | 2026-02-23 | 2026-02-27 | Samiksha | Development | 3-Completed | 6 | 1 | 1 | 2 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US3 | T8 | Implement regex-based preprocessing for filtering and cleaning input text data | 2026-02-23 | 2026-02-26 | Samiksha | Development | 3-Completed | 4 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US4 | T9 | Integrate loader with parallel processing module and validate chunking mechanism | 2026-02-27 | 2026-03-04 | Samiksha | Development | 3-Completed | 5 | 0 | 0 | 1 | 2 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US5 | T10 | Perform system testing on large datasets and debug performance or logical issues | 2026-03-04 | 2026-03-08 | Samiksha | Testing | 3-Completed | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 2 | 1
SPRINT 3 BACKLOG
US6 | T11 | Design rule-based sentiment scoring logic including lexicons and scoring thresholds | 2026-03-09 | 2026-03-12 | Samiksha | Design | 3-Completed | 4 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US6 | T12 | Implement parallel sentiment scoring engine using rule-based logic | 2026-03-11 | 2026-03-14 | Samiksha | Development | 3-Completed | 5 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US7 | T13 | Store processed and scored data into SQLite database with proper schema | 2026-03-12 | 2026-03-16 | Samiksha | Development | 3-Completed | 4 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US7 | T14 | Develop search interface with filtering and CSV export functionality | 2026-03-16 | 2026-03-18 | Samiksha | Development | 3-Completed | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0
US8 | T15 | Integrate email notification system for automated report sharing | 2026-03-18 | 2026-03-19 | Samiksha | Integration | 3-Completed | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 2
SPRINT 4 BACKLOG
US9 | T16 | Implement inverted index to improve search efficiency for large datasets | 2026-03-20 | 2026-03-23 | Samiksha | Development | 3-Completed | 4 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US9 | T17 | Enable dynamic index updates for new incoming text data | 2026-03-23 | 2026-03-25 | Samiksha | Development | 3-Completed | 3 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US10 | T18 | Perform performance testing on large-scale datasets and optimize execution time | 2026-03-24 | 2026-03-26 | Samiksha | Testing | 3-Completed | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0
US10 | T19 | Final integration of all modules, code review, and complete documentation | 2026-03-26 | 2026-03-31 | Samiksha | Integration | 3-Completed | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1
Note on D2: ====== ID#AAABcShYZRI Please enter the dates in either of these formats (2025-01-27 09:44:41) 9/15/2016 or 15-Sep-2016
Note on E2: ====== ID#AAABcShYZRU Please enter the dates in either of these formats (2025-01-27 09:44:41) 9/15/2016 or 15-Sep-2016
Note on I3: ====== ID#AAABcShYZQ4 Sumeet Kumar Barua08 (2025-01-27 09:44:41) This is the total task estimated in hours for all the user stories
Note on J3: ====== ID#AAABcShYZRc Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 1 work
Note on K3: ====== ID#AAABcShYZRg Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 2 work
Note on L3: ====== ID#AAABcShYZQs Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 3 work
Note on M3: ====== ID#AAABcShYZRo Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 4 work
Note on N3: ====== ID#AAABcShYZQw Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 5 work
Note on O3: ====== ID#AAABcShYZRk Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 6 work
Note on P3: ====== ID#AAABcShYZRY Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 7 work
Note on Q3: ====== ID#AAABcShYZRA Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 8 work
Note on R3: ====== ID#AAABcShYZRs Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 9 work
Note on S3: ====== ID#AAABcShYZRM Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 10 work
Note on T3: ====== ID#AAABcShYZRE Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 11 work
Note on U3: ====== ID#AAABcShYZQ8 Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 12 work
Note on V3: ====== ID#AAABcShYZQ0 Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 13 work
Note on W3: ====== ID#AAABcShYZRQ Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 14 work

## Stand up Meeting
Sprint | Day | Impediments | Action Taken
Sprint 1 | Day 2 | Environment setup issues | Reinstalled Python and dependencies
Sprint 1 | Day 10 | Difficulty understanding multiprocessing | Referred documentation and tutorials
Sprint 2 | Day 16 | Large file handling slow | Introduced batch processing
Sprint 2 | Day 22 | Memory issues | Optimized chunk size
Sprint 3 | Day 30 | Incorrect sentiment scoring | Refined rules and tested cases
Sprint 3 | Day 39 | Search results slow | Added indexing
Sprint 4 | Day 44 | Database query delay | Optimized queries
Sprint 4 | Day 53 | Email integration error | Fixed API configuration

## Retrospection
SL # | Sprint # | Sprint start date | Sprint end date | Team member name | Start Doing | Stop Doing | Continue Doing | Action taken
1 | Sprint 1 | 2026-02-09 | 2026-02-15 | Rutuja , Shelly,Shaliha | Start planning tasks clearly | Stop unstructured setup | Continue team discussions | Created proper project setup and workflow
2 | Sprint 1 | 2026-02-16 | 2026-02-21 | Rutuja , Shelly,Shaliha | Start learning multiprocessing | Stop confusion in concepts | Continue self-learning | Referred documentation and practiced examples
3 | Sprint 2 | 2026-02-23 | 2026-02-26 | Rutuja , Shelly,Shaliha | Start implementing chunk processing | Stop processing full dataset at once | Continue modular coding | Improved performance using batch processing
4 | Sprint 2 | 2025-02-27 | 2029-03-07 | Rutuja , Shelly,Shaliha | Start validating input data | Stop ignoring edge cases | Continue testing with datasets | Added validation checks
5 | Sprint 3 | 2026-03-08 | 2026-03-11 | Rutuja , Shelly,Shaliha | Start improving scoring accuracy | Stop using basic rules only | Continue refining logic | Added negation and intensifier rules
6 | Sprint 3 | 2026-03-12 | 2026-03-19 | Rutuja , Shelly,Shaliha | Start optimizing search filters | Stop slow queries | Continue debugging | Improved filtering performance
7 | Sprint 4 | 2026-03-20 | 2026-03-23 | Rutuja , Shelly,Shaliha | Start database optimization | Stop inefficient queries | Continue indexing approach | Implemented indexing for faster queries
8 | Sprint 4 | 2026-03-24 | 2026-03-29 | Rutuja , Shelly,Shaliha | Start integration and testing | Stop isolated module testing | Continue collaboration | Integrated all modules successfully